## Sheet1
Workout Buddy Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate
Sptint #1 4/4/2016
User Login |  |  | Complete
User Registration |  |  | Complete
Profile Page |  |  | Complete
User Add grous public/private groups |  |  | Complete
Sptint #1 4/5/2016
User Add members to group |  |  | Complete
User Add grous public/private groups |  |  | Complete
Join a public group |  |  | Complete
Sptint #1 4/6/2016
Add Bootstrap theme |  |  | Complete
User Add members to group |  |  | Complete
Members sent messages (sent) |  |  | Complete
Add Challenge |  |  | Complete
Sptint #1 4/7/2016
Group profile page display all members |  |  | Complete
Find group by category |  |  | Complete
Members receive messages (inbox) |  |  | Complete
View Challenge |  |  | Complete
Sptint #1 4/8/2016
Leave a public group |  |  | Complete
Documentation PHP Doc |  |  | Complete
Documentation UML |  |  | Complete
Documentation PPT |  |  | Complete
Total