## Sheet1
Workout Buddy Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
User Login |  | Yes | High | Complete |  | Yes
User Registration |  | Yes | High | Complete |  | Yes
Send email for activation of acount |  | No | Low | Not Started |  | No
Password Recovery |  | No | Medium | Not Started |  | No
Profile Page |  | Yes | High | Complete |  | Yes
User Add grous public/private groups |  | Yes | High | Complete
User Add members to group |  | Yes | High | Complete
Group profile page display all members |  | Yes | High | In Progress
Message members |  |  | Medium | In Progress
Members receive messages (inbox) |  |  | Medium | In Progress
Members sent messages (sent) |  |  | Medium | In Progress

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started