## Sheet1
Workout Buddy Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
User Login |  | Yes | High | Complete |  | Yes
User Registration |  | Yes | High | Complete |  | Yes
Log user login in log file |  | No | Low | Not Started |  | No
Send email for activation of acount |  | No | Low | Not Started |  | No
Password Recovery |  | No | Medium | Not Started |  | No
Profile Page |  | Yes | High | Complete |  | Yes
User Add groups public/private groups |  | Yes | High | Complete |  | Yes
User Add members to group |  | Yes | High | Complete |  | Yes
Find group by category |  | Yes | High | Complete |  | Yes
Join a public group |  | Yes | High | Complete |  | Yes
Leave a public group |  | Yes | High | Complete |  | Yes
Group profile page display all members |  | Yes | High | Complete |  | Yes
Message members |  | Yes | Medium | In Progress |  | Yes
Members receive messages (inbox) |  | Yes | Medium | In Progress |  | Yes
Members sent messages (sent) |  | Yes | Medium | In Progress |  | Yes
Private group invite |  | No | Low | Not Started |  | No
Add Challenge |  | Yes | Low | Complete |  | Yes
View Challenge |  | Yes | Low | Complete |  | Yes
Add Bootstrap theme |  | Yes | High | Complete |  | Yes
Add Routine |  | Yes | High | In Progress |  | No
Start Routine |  | Yes | High | Complete |  | Yes
View Routine |  | Yes | High | Complete |  | No
Add Calendar |  | Yes | High | Complete |  | No
Add Calendar Event |  | Yes | High | Complete |  | Yes
Add Routine Days to Calendar Event |  | Yes | High | Complete |  | Yes
Add Start Date and End Date |  | Yes | High | Complete |  | Yes
Exercise Database/Images |  | Yes | High | Complete |  | Yes
Edit Routine |  | Yes | High | In Progress |  | Yes
Add Exercise |  | Yes | High | Complete |  | Yes
Edit Exercise |  | Yes | High | Complete |  | Yes
Add Log event |  | Yes | High | Complete |  | Yes
View Log event |  | Yes | High | In Progress |  | Yes
Add Agenda |  | Yes | High | Complete |  | Yes
View Exercise |  | Yes | High | In Progress |  | Yes
Add Group feature for Exercise |  | Yes | Medium | Not Started |  | No
Delete Routine |  | Yes | High | In Progress |  | Yes
Delete Routine/Delete All Calendar Events |  | Yes | High | Complete |  | Yes
Analytics: Improvement Analysis |  | Yes | High | Complete |  | Yes
Analytics: Strengh Growth Analysis |  | Yes | High | Complete |  | Yes
Analytics: Workout History |  | Yes | High | Complete |  | Yes
Documentation/Maintenance Plan |  | Yes | High | Complete |  | Yes
Documentation/Deployment Plan |  | Yes | High | In Progress |  | Yes
Documentation/User's Manual |  | Yes | High | Not Started |  | Yes
About/Contact Page |  | Yes | Low | In Progress |  | Yes

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started