## Sheet1
Workout Buddy Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate
Sptint #1 4/4/2016
User Login |  |  | Complete
User Registration |  |  | Complete
Profile Page |  |  | Complete
User Add grous public/private groups |  |  | Complete
Sptint #2 4/5/2016
User Add members to group |  |  | Complete
User Add grous public/private groups |  |  | Complete
Join a public group |  |  | Complete
Sptint #3 4/6/2016
Add Bootstrap theme |  |  | Complete
User Add members to group |  |  | Complete
Members sent messages (sent) |  |  | Complete
Add Challenge |  |  | Complete
Sptint #4 4/7/2016
Group profile page display all members |  |  | Complete
Find group by category |  |  | Complete
Members receive messages (inbox) |  |  | Complete
View Challenge |  |  | Complete
Sptint #5 4/8/2016
Leave a public group |  |  | Complete
Documentation PHP Doc |  |  | Complete
Documentation UML |  |  | Complete
Documentation PPT |  |  | Complete
Sptint #6 4/11/2016 - 4/15/2016
Add Calendar |  |  | Complete
Add Routine |  |  | Complete
View Routine |  |  | Complete
Sptint #6 4/16/2016 - 4/17/2016
Add Start Date and End Date |  |  | Complete
Delete Routine |  |  | Complete
Exercise Database/Images |  |  | Complete
Documentation/Maintenance Plan |  |  | Complete
Sptint #6 4/18/2016 - 4/22/2015
Add Calendar Event |  |  | Complete
Add Routine Days to Calendar Event |  |  | Complete
Delete Routine |  |  | Complete
Delete Routine/Delete All Calendar Events |  |  | Complete
Add Exercise |  |  | Complete
Edit Exercise |  |  | Complete
Edit Routine |  |  | Complete
Add Log event |  |  | Complete
Add Agenda |  |  | Complete
Analytics: Improvement Analysis |  |  | Complete
Analytics: Strengh Growth Analysis |  |  | Complete
Analytics: Workout History |  |  | Complete
Sptint #6 4/23/2016 - 4/24/2015
Start routine pagination |  |  | Complete
Start Routine |  |  | Complete
View Log
Sptint #6 4/25/2016 - 4/29/2015
Testing
Documentation/Deployment Plan
Bug fixers
About/Contact Page
Sptint #6 4/30/2016 - 5/5/2015
Documentation/User's Manual
Total